## Project Planner
OpenSpace Project Planner
Project timeline: Aug 2026 - July 2027 ¦ Updated: 11 Aug 2026 ¦ Monthly Gantt Chart (August) | [5 empty] | Period Highlight: | 2026-08-01 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | Owner | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 2026-08-01 | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-08-31
Project kickoff and role allocation | Project Team | 2026-08-07 | 1 | 2026-08-07 | 1 | 100%
OpenSpace portal and functionality research | Hein Myat Thu | 2026-08-08 | 3 | 2026-08-08 | 2 | 100%
Initial frontend wireframe design | Hein Myat Thu | 2026-08-11 | 2 | 2026-08-10 | 1 | 100%
Provider API and specification review (TBC) | Project Team | 2026-08-20 |  |  |  | 0%
Activity 05 | [5 empty] | 0%
Activity 06 | [5 empty] | 0%
Activity 07 | [5 empty] | 0%
Activity 08 | [5 empty] | 0%
Activity 09 | [5 empty] | 0%
Activity 10 | [5 empty] | 0%
Activity 11 | [5 empty] | 0%
Activity 12 | [5 empty] | 0%
Activity 13 | [5 empty] | 0%
Activity 14 | [5 empty] | 0%
Activity 15 | [5 empty] | 0%
Activity 16 | [5 empty] | 0%
Activity 17 | [5 empty] | 0%
Activity 18 | [5 empty] | 0%
Activity 19 | [5 empty] | 0%
Activity 20 | [5 empty] | 0%
Activity 21 | [5 empty] | 0%
Activity 22 | [5 empty] | 0%
Activity 23 | [5 empty] | 0%
Activity 24 | [5 empty] | 0%
Activity 25 | [5 empty] | 0%
Activity 26 | [5 empty] | 0%